## Phase1 Tasks
| ID | Task Description | Status | Assigned To | Depends on | Comment
x | 1 | Get to know your team members. Send them your email, or meet them in class or even outside of class | Completed | Team | None
x | 2 | discuss this project and who will take on what role (task) in the team. | Completed | Team | None
x | 3 | Create a Github.com or Google code hosted account if you have not already done that and | Completed | Team | None
x | 4 | invite all the team members to join that account (everyone will need an account to join). | Completed | Team | None
| 5 | Find the C source code for a hello world program and copy the text to a .c source file. A link to one is http://groups.engin.umd.umich.edu/CIS/course.des/cis400/c/ hworld.html. | Completed | Tim | None
| 6 | Write a Make file that compiles this program file into a program called “hello”. The Linux lab manual has some information on this. | Completed | Tim | 5
x | 7 | Setup the code repository account with the source file and the make file | Completed | Tim | None
x | 8 | have every team member check out the project and change or add a source code comment in either file. Each team member must then commit their changes back to the repository. | In Progress | Team
x | 9 | Take a screenshot of the source changes page of the repository website showing how each team member has committed to the source. Provide an explanation below the screenshot identifying which team member relates to which id in the repository. | Not Started | Vivian |  | change-screenshot.docx
| 10 | Use make to compile your program and paste the terminal output into your solution document. If you redirect stdout to a file this process may be easier. | Not Started | Nick | 5, 6 | solution-document.docx
| 11 | Use GDB to set a breakpoint at the main function, then step through your program. It should only have one line in the code so this shouldn’t take long. Paste the terminal output to your solution document. | Not Started | Nick | 5, 6 | solution-document.docx
| 12 | Run your application and paste the terminal output into your solution document. | Not Started | Nick | 5, 6 | solution-document.docx
| 13 | create a pseudocode design for each function of the program outlined in the problem statement. | In Progress | Vivian | None | pseudocode-design.docx
| 14 | create a test design document outlining the tests you will run for each functional test. This should be put into a spreadsheet where each row is the test you will run and the columns are as follows: for each parameter you will need one column for each partition class, the final column is your expected output. | In Progress | Vivian | None | test-design.xlsx
| 15 | Put your solution document (answers to the questions), your source code file (hello world source), your make file, the compiled program, all of your pdf design documents (which includes your planned tests) into a tarball archive file. | Not Started | Vivian | 1-14 | cse220_lab2_phase1.tar

## Phase2 Tasks
| ID | Task Description | Status | Assigned To | Depends on | Comment
x | 1 | You will need to have code for each test case,
x | 2 | as well as, code for the program as well.
x | 3 | your source code must be split into two files, one where all the print functions exist,
x | 4 | and the second where you have all other functions.
| 5 | There must be a single header file for functions prototypes and global constants.
| 6 | You must have a make file for your implementation, which compiles your code into an executable called “lister”.
x | 7 | you can gain some of your points back by providing a bug report.
x | 8
x | 9
10
11
12
13
14
15